## ProjectSchedule_draft
Mechanical and Electrical Works Draft Work Schedule
EVEX Clinic
|  | Project Start: | 2018-06-06
|  | Display Week: | 1 | [6 empty] | 2018-06-04 | [6 empty] | 2018-06-11 | [6 empty] | 2018-06-18 | [6 empty] | 2018-06-25 | [6 empty] | 2018-07-02 | [6 empty] | 2018-07-09 | [6 empty] | 2018-07-16 | [6 empty] | 2018-07-23 | [6 empty] | 2018-07-30 | [6 empty] | 2018-08-06 | [6 empty] | 2018-08-13 | [6 empty] | 2018-08-20 | [6 empty] | 2018-08-27 | [6 empty] | 2018-09-03 | [6 empty] | 2018-09-10 | [6 empty] | 2018-09-17 | [6 empty] | 2018-09-24 | [6 empty] | 2018-10-01 | [6 empty] | 2018-10-08 | [6 empty] | 2018-10-15 | [6 empty] | 2018-10-22
 | time axis 2018-06-04 to 2018-10-28
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | NO.of EMPLOYEE | MAN HOUR | NOTEs | DAYS | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ | ო | ს | ო | ხ | პ | შ | კ
LEVEL (-2) |  |  | 2018-06-10 | 2018-09-09 | 92 |  | 8847 |  | 92
Electrical works (ელექტროობა) |  | 0% | 2018-06-10 | 2018-08-20 | 72 |  | 1440 |  | 72
Cable tray installation |  | 0% | 2018-06-10 | 2018-06-20 | 11 | 4 | 396 | Team 1 | 11
Cabling works |  | 0% | 2018-07-10 | 2018-07-16 | 7 | 4 | 252 | Team 3 | 7
Installation of floor distribution boards and termination works |  | 0% | 2018-07-15 | 2018-07-25 | 11 | 4 | 396 | Team 5 | 11
Lighting and fixtures installation |  | 0% | 2018-08-10 | 2018-08-20 | 11 | 4 | 396 | Team 7 | 11
Ventilation (ვენტილაცია) |  | 0% | 2018-06-15 | 2018-07-10 | 26 |  | 1701 |  | 26
Workshop production of air ducts |  | 0% | 2018-06-15 | 2018-06-25 | 11 | 5 | 495 | WS Team | 11
Insulation of fresh air ducts |  | 0% | 2018-06-26 | 2018-06-30 | 5 | 6 | 270 | Isolat. Team | 5
Installation of air ducts |  | 0% | 2018-06-28 | 2018-07-10 | 13 | 8 | 936 | Inst. Team - 1 | 13
Heating & Cooling (გათბობა-გაგრილება) |  | 0% | 2018-06-15 | 2018-07-25 | 41 |  | 1368 |  | 41
Piping works |  | 0% | 2018-06-15 | 2018-06-30 | 16 | 4 | 576 | Team 1 | 16
Insulation of pipes |  | 0% | 2018-06-20 | 2018-06-30 | 11 | 3 | 297 | Team 3 | 11
Installation of FCUs and connection of pipes, valves..etc. |  | 0% | 2018-07-15 | 2018-07-25 | 11 | 5 | 495 | Team 5 | 11
Water & Sewage (კანალიზაცია) |  | 0% | 2018-06-15 | 2018-07-20 | 40 |  | 1368 |  | 36
PPR and PVC piping works |  | 0% | 2018-06-15 | 2018-06-30 | 16 | 5 | 720 | Team 1 | 16
Steel piping works |  | 0% | 2018-06-16 | 2018-07-03 | 18 | 4 | 648 | Team 2 | 18
Installation of accessories |  | 0% | 2018-07-15 | 2018-07-20 | 6 | 4 | 216 | Team 3
Fire fighting system (სახანძრო უსაფრთხოება) |  | 0% | 2018-07-20 | 2018-09-09 | 52 |  | 2250 |  | 52
Piping works |  | 0% | 2018-07-20 | 2018-08-25 | 37 | 6 | 1998 | Team 1 | 37
Fire cabinet and sprinkler installations |  |  | 2018-08-27 | 2018-09-09 | 14 | 2 | 252 | Team 2 | 14
Weak current (სუსტი დენები) |  | 0% | 2018-06-13 | 2018-07-02 | 20 |  | 720 |  | 20
Data and Internet cabling |  |  | 2018-06-13 | 2018-07-02 | 20 | 4 | 720 | Team 1 | 20
Fire alarm system network
Surround voice systems
LEVEL (-1) |  |  | 2018-06-11 | 2018-09-09 | 91 |  | 9171
Electrical works (ელექტროობა) |  | 0% | 2018-06-11 | 2018-08-24 | 75 |  | 1548
Cable tray installation |  | 0% | 2018-06-11 | 2018-06-21 | 11 | 4 | 396 | Team 2
Cabling works |  | 0% | 2018-07-14 | 2018-07-21 | 8 | 4 | 288 | Team 4
Installation of floor distribution boards and termination works |  | 0% | 2018-07-20 | 2018-07-30 | 11 | 4 | 396 | Team 6
Lighting and fixtures installation |  | 0% | 2018-08-12 | 2018-08-24 | 13 | 4 | 468 | Team 8
Ventilation (ვენტილაცია) |  |  | 2018-06-15 | 2018-07-10 | 26 |  | 1701
Workshop production of air ducts |  |  | 2018-06-15 | 2018-06-25 | 11 | 5 | 495 | WS Team
Insulation of fresh air ducts |  |  | 2018-06-26 | 2018-06-30 | 5 | 6 | 270 | Isolat. Team
Installation of air ducts |  |  | 2018-06-28 | 2018-07-10 | 13 | 8 | 936 | Inst. Team -1
Heating & Cooling (გათბობა-გაგრილება) |  |  | 2018-06-15 | 2018-07-25 | 41 |  | 1368
Piping works |  |  | 2018-06-15 | 2018-06-30 | 16 | 4 | 576 | Team 1
Insulation of pipes |  |  | 2018-06-20 | 2018-06-30 | 11 | 3 | 297 | Team 3
Installation of FCUs and connection of pipes, valves..etc. |  |  | 2018-07-15 | 2018-07-25 | 11 | 5 | 495 | Team 5
Water & Sewage (კანალიზაცია) |  |  | 2018-06-15 | 2018-07-20 | 36 |  | 1584
PPR and PVC piping works |  |  | 2018-06-15 | 2018-06-30 | 16 | 5 | 720 | Team 1
Steel piping works |  |  | 2018-06-16 | 2018-07-03 | 18 | 4 | 648 | Team 2
Installation of accessories |  |  | 2018-07-15 | 2018-07-20 | 6 | 4 | 216 | Team 3
Fire fighting system (სახანძრო უსაფრთხოება) |  |  | 2018-07-20 | 2018-09-09 | 52 |  | 2250
Piping works |  |  | 2018-07-20 | 2018-08-25 | 37 | 6 | 1998 | Team 1
Fire cabinet and sprinkler installations |  |  | 2018-08-27 | 2018-09-09 | 14 | 2 | 252 | Team 2
Weak current (სუსტი დენები) |  |  | 2018-06-16 | 2018-07-05 | 20 |  | 720
Data and Internet cabling |  |  | 2018-06-16 | 2018-07-05 | 20 | 4 | 720 | Team 2
Fire alarm system network
Surround voice systems
LEVEL (1) |  |  | 2018-06-15 | 2018-09-05 | 83 |  | 9477
Electrical works (ელექტროობა) |  | 0% | 2018-06-21 | 2018-09-05 | 77 |  | 1800
Cable tray installation |  | 15% | 2018-06-21 | 2018-07-01 | 11 | 4 | 396 | Team 1
Cabling works |  | 20% | 2018-07-17 | 2018-07-27 | 11 | 4 | 396 | Team 3
Installation of floor distribution boards and termination works |  | 5% | 2018-07-26 | 2018-08-06 | 12 | 4 | 432 | Team 5
Lighting and fixtures installation |  | 35% | 2018-08-21 | 2018-09-05 | 16 | 4 | 576 | Team 7
Ventilation (ვენტილაცია) |  |  | 2018-06-26 | 2018-07-18 | 23 |  | 2007
Workshop production of air ducts |  | 0% | 2018-06-26 | 2018-07-02 | 7 | 5 | 315 | WS Team
Insulation of fresh air ducts |  | 0% | 2018-07-01 | 2018-07-10 | 10 | 6 | 540 | Isolat. Team
Installation of air ducts |  | 0% | 2018-07-03 | 2018-07-18 | 16 | 8 | 1152 | Inst. Team - 2
Heating & Cooling (გათბობა-გაგრილება) |  |  | 2018-06-15 | 2018-07-15 | 31 |  | 2097
Piping works |  |  | 2018-06-15 | 2018-07-05 | 21 | 4 | 756 | Team 2
Insulation of pipes |  |  | 2018-07-01 | 2018-07-15 | 15 | 3 | 405 | Team 3
Installation of FCUs and connection of pipes, valves..etc. |  |  | 2018-06-20 | 2018-07-15 | 26 | 4 | 936 | Team 6
Water & Sewage (კანალიზაცია) |  |  | 2018-07-01 | 2018-08-07 | 38 |  | 2169
PPR and PVC piping works |  |  | 2018-07-01 | 2018-07-17 | 17 | 5 | 765 | Team 1
Steel piping works |  |  | 2018-07-04 | 2018-07-24 | 21 | 4 | 756 | Team 2
Installation of accessories |  |  | 2018-07-21 | 2018-08-07 | 18 | 4 | 648 | Team 3
Fire fighting system (სახანძრო უსაფრთხოება) |  |  | 2018-07-15 | 2018-08-01 | 18 |  | 648
Piping works |  |  | 2018-07-15 | 2018-08-01 | 18 | 2 | 324 | Team 3
Fire cabinet installation |  |  | 2018-07-15 | 2018-08-01 | 18 | 2 | 324
Weak current (სუსტი დენები) |  |  | 2018-07-03 | 2018-07-23 | 21 |  | 756
Data and Internet cabling |  |  | 2018-07-03 | 2018-07-23 | 21 | 4 | 756 | Team 1
Fire alarm system network
Surround voice systems
LEVEL (2) |  |  | 2018-06-22 | 2018-09-12 | 83 |  | 9972
Electrical works (ელექტროობა) |  | 0% | 2018-06-22 | 2018-09-10 | 81 |  | 1944
Cable tray installation |  | 0% | 2018-06-22 | 2018-07-02 | 11 | 4 | 396 | Team 2
Cabling works |  | 0% | 2018-07-22 | 2018-08-03 | 13 | 4 | 468 | Team 4
Installation of floor distribution boards and termination works |  | 0% | 2018-08-01 | 2018-08-13 | 13 | 4 | 468 | Team 6
Lighting and fixtures installation |  | 0% | 2018-08-25 | 2018-09-10 | 17 | 4 | 612 | Team 8
Ventilation (ვენტილაცია) |  |  | 2018-07-03 | 2018-07-25 | 23 |  | 2034
Workshop production of air ducts |  |  | 2018-07-03 | 2018-07-10 | 8 | 5 | 360 | WS Team
Insulation of fresh air ducts |  |  | 2018-07-10 | 2018-07-20 | 11 | 6 | 594 | Isolat. Team
Installation of air ducts |  |  | 2018-07-11 | 2018-07-25 | 15 | 8 | 1080 | Inst. Team - 1
Heating & Cooling (გათბობა-გაგრილება) |  |  | 2018-06-26 | 2018-08-03 | 39 |  | 2313
Piping works |  |  | 2018-07-01 | 2018-07-25 | 25 | 4 | 900 | Team 1
Insulation of pipes |  |  | 2018-07-16 | 2018-08-03 | 19 | 3 | 513 | Team 3
Installation of FCUs and connection of pipes, valves..etc. |  |  | 2018-06-26 | 2018-07-20 | 25 | 4 | 900 | Team 5
Water & Sewage (კანალიზაცია) |  |  | 2018-07-18 | 2018-09-05 | 50 |  | 2277
PPR and PVC piping works |  |  | 2018-07-18 | 2018-08-03 | 17 | 5 | 765 | Team 1
Steel piping works |  |  | 2018-07-25 | 2018-08-15 | 22 | 4 | 792 | Team 2
Installation of accessories |  |  | 2018-08-17 | 2018-09-05 | 20 | 4 | 720 | Team 4
Fire fighting system (სახანძრო უსაფრთხოება) |  |  | 2018-08-26 | 2018-09-12 | 18 |  | 648
Piping works |  |  | 2018-08-26 | 2018-09-12 | 18 | 2 | 324 | Team 1
Fire cabinet installation |  |  | 2018-08-26 | 2018-09-12 | 18 | 2 | 324
Weak current (სუსტი დენები) |  |  | 2018-07-06 | 2018-07-26 | 21 |  | 756
Data and Internet cabling |  |  | 2018-07-06 | 2018-07-26 | 21 | 4 | 756 | Team 2
Fire alarm system network
Surround voice systems
LEVEL (3) |  |  | 2018-07-02 | 2018-09-18 | 79 |  | 10530
Electrical works (ელექტროობა) |  | 20% | 2018-07-02 | 2018-09-18 | 79 |  | 1800
Cable tray installation |  | 15% | 2018-07-02 | 2018-07-12 | 11 | 4 | 396 | Team 1
Cabling works |  | 20% | 2018-07-28 | 2018-08-09 | 13 | 4 | 468 | Team 3
Installation of floor distribution boards and termination works |  | 35% | 2018-08-07 | 2018-08-19 | 13 | 4 | 468 | Team 5
Lighting and fixtures installation |  | 5% | 2018-09-06 | 2018-09-18 | 13 | 4 | 468 | Team 7
Ventilation (ვენტილაცია) |  |  | 2018-07-11 | 2018-08-10 | 31 |  | 2610
Workshop production of air ducts |  |  | 2018-07-11 | 2018-07-18 | 8 | 5 | 360 | WS Team
Insulation of fresh air ducts |  |  | 2018-07-21 | 2018-07-31 | 11 | 6 | 594 | Isolat. Team
Installation of air ducts |  |  | 2018-07-19 | 2018-08-10 | 23 | 8 | 1656 | Inst. Team - 2
Heating & Cooling (გათბობა-გაგრილება) |  |  | 2018-07-05 | 2018-08-20 | 47 |  | 2367
Piping works |  |  | 2018-07-05 | 2018-08-01 | 28 | 4 | 1008 | Team 2
Insulation of pipes |  |  | 2018-08-04 | 2018-08-20 | 17 | 3 | 459 | Team 3
Installation of FCUs and connection of pipes, valves..etc. |  |  | 2018-07-17 | 2018-08-10 | 25 | 4 | 900 | Team 6
Water & Sewage (კანალიზაცია) |  |  | 2018-08-04 | 2018-09-05 | 33 |  | 2349
PPR and PVC piping works |  |  | 2018-08-04 | 2018-08-24 | 21 | 5 | 945 | Team 1
Steel piping works |  |  | 2018-08-16 | 2018-09-05 | 21 | 4 | 756 | Team 2
Installation of accessories |  |  | 2018-08-08 | 2018-08-25 | 18 | 4 | 648 | Team 3
Fire fighting system (სახანძრო უსაფრთხოება) |  |  | 2018-08-02 | 2018-08-19 | 18 |  | 648
Piping works |  |  | 2018-08-02 | 2018-08-19 | 18 | 2 | 324 | Team 3
Fire cabinet installation |  |  | 2018-08-02 | 2018-08-19 | 18 | 2 | 324
Weak current (სუსტი დენები) |  |  | 2018-07-24 | 2018-08-13 | 21 |  | 756
Data and Internet cabling |  |  | 2018-07-24 | 2018-08-13 | 21 | 4 | 756 | Team 1
Fire alarm system network
Surround voice systems
LEVEL (4) |  |  | 2018-07-03 | 2018-09-25 | 85 |  | 11079
Electrical works (ელექტროობა) |  | 20% | 2018-07-03 | 2018-09-25 | 85 |  | 1836
Cable tray installation |  | 15% | 2018-07-03 | 2018-07-13 | 11 | 4 | 396 | Team 2
Cabling works |  | 20% | 2018-08-04 | 2018-08-15 | 12 | 4 | 432 | Team 4
Installation of floor distribution boards and termination works |  | 5% | 2018-08-14 | 2018-08-26 | 13 | 4 | 468 | Team 6
Lighting and fixtures installation |  | 105% | 2018-09-11 | 2018-09-25 | 15 | 4 | 540 | Team 8
Ventilation (ვენტილაცია) |  |  | 2018-07-19 | 2018-08-15 | 28 |  | 2727
Workshop production of air ducts |  |  | 2018-07-19 | 2018-07-27 | 9 | 5 | 405 | WS Team
Insulation of fresh air ducts |  |  | 2018-08-01 | 2018-08-15 | 15 | 6 | 810 | Isolat. Team
Installation of air ducts |  |  | 2018-07-26 | 2018-08-15 | 21 | 8 | 1512 | Inst. Team - 1
Heating & Cooling (გათბობა-გაგრილება) |  |  | 2018-07-21 | 2018-09-15 | 57 |  | 2754
Piping works |  |  | 2018-07-26 | 2018-08-26 | 32 | 4 | 1152 | Team 1
Insulation of pipes |  |  | 2018-08-21 | 2018-09-15 | 26 | 3 | 702 | Team 3
Installation of FCUs and connection of pipes, valves..etc. |  |  | 2018-07-21 | 2018-08-14 | 25 | 4 | 900 | Team 5
Water & Sewage (კანალიზაცია) |  |  | 2018-08-25 | 2018-09-25 | 32 |  | 2358
PPR and PVC piping works |  |  | 2018-08-25 | 2018-09-15 | 22 | 5 | 990 | Team 1
Steel piping works |  |  | 2018-09-06 | 2018-09-23 | 18 | 4 | 648 | Team 2
Installation of accessories |  |  | 2018-09-06 | 2018-09-25 | 20 | 4 | 720 | Team 4
Fire fighting system (სახანძრო უსაფრთხოება) |  |  | 2018-08-20 | 2018-09-06 | 18 |  | 648
Piping works |  |  | 2018-08-20 | 2018-09-06 | 18 | 2 | 324 | Team 3
Fire cabinet installation |  |  | 2018-08-20 | 2018-09-06 | 18 | 2 | 324
Weak current (სუსტი დენები) |  |  | 2018-07-27 | 2018-08-16 | 21 |  | 756
Data and Internet cabling |  |  | 2018-07-27 | 2018-08-16 | 21 | 4 | 756 | Team 2
Fire alarm system network
Surround voice systems
ROOF (TECHNICAL FLOOR) |  |  | 2018-07-13 | 2018-09-30 | 80 |  | 22653
Electrical works (ელექტროობა) |  | 0% | 2018-07-13 | 2018-09-30 | 80 |  | 2700
Cable tray installation |  | 0% | 2018-07-13 | 2018-07-25 | 13 | 4 | 468 | Team 1
Cabling works |  | 0% | 2018-08-10 | 2018-09-01 | 23 | 4 | 828 | Team 3 | Team 4
Installation of floor distribution boards and termination works |  | 0% | 2018-08-20 | 2018-09-15 | 27 | 4 | 972 | Team 5
Lighting and fixtures installation |  | 0% | 2018-09-19 | 2018-09-30 | 12 | 4 | 432 | Team 6
Ventilation (ვენტილაცია) |  |  | 2018-07-28 | 2018-09-30 | 65 |  | 7353
Workshop production of air ducts |  |  | 2018-07-28 | 2018-09-10 | 45 | 5 | 2025 | WS Team
Insulation of fresh air ducts |  |  | 2018-08-16 | 2018-09-16 | 32 | 6 | 1728 | Isolat. Team
Installation of air ducts |  |  | 2018-08-12 | 2018-09-30 | 50 | 8 | 3600 | Inst. Team - 1 + 2
Heating & Cooling (გათბობა-გაგრილება) |  |  | 2018-08-01 | 2018-09-30 | 61 |  | 9270
Piping works |  |  | 2018-08-01 | 2018-09-30 | 61 | 8 | 4392 | Team 2 + 1
Insulation of pipes |  |  | 2018-08-05 | 2018-09-30 | 57 | 6 | 3078 | Team 4 + 3
Installation of FCUs and connection of pipes, valves..etc. |  |  | 2018-08-12 | 2018-09-30 | 50 | 4 | 1800 | Team 6 + 5
Water & Sewage (კანალიზაცია) |  |  | 2018-08-27 | 2018-09-30 | 35 |  | 1116
PPR and PVC piping works |  |  | 2018-09-16 | 2018-09-27 | 12 | 5 | 540 | Team 1
Steel piping works |  |  | 2018-09-24 | 2018-09-30 | 7 | 4 | 252 | Team 2
Installation of accessories |  |  | 2018-08-27 | 2018-09-04 | 9 | 4 | 324 | Team 3
Fire fighting system (სახანძრო უსაფრთხოება) |  |  | 2018-09-07 | 2018-09-30 | 24 |  | 1026
Piping works |  |  | 2018-09-07 | 2018-09-30 | 24 | 4 | 864 | Team 3
Fire cabinet installation |  |  | 2018-09-07 | 2018-09-15 | 9 | 2 | 162
Weak current (სუსტი დენები) |  |  | 2018-08-14 | 2018-09-15 | 33 |  | 1188
Data and Internet cabling |  |  | 2018-08-14 | 2018-09-15 | 33 | 4 | 1188 | Team 2
Fire alarm system network
Surround voice systems
TEST and COMMISIONING |  |  | 2018-09-01 | 2018-09-15 | 15 |  | 1350
Mechanical systems testing and commisioning |  |  | 2018-09-01 | 2018-09-15 | 15 | 10 | 1350
Weak current systems testing and commisioning
Electrical systems testing and commisioning
Fire fighting systems testing and commisioning
Ventilation testing and commisioning
Heating & Cooling testing and commisioning
Note on K6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.